## LEDGER
Cost Code | Date | Invoice # | Payee | Description | Amount | Amount Paid | Amount Due | Funding Source
0.0001 |  |  | Disbursement #00 |  | 593250 | 593250 |  | VENTANAS I
0.0002 |  |  | Disbursement #00 |  | 7507599.7 | 7507599.7 |  | VENTANAS I
0.0002 |  |  | Disbursement #00 |  | 1875000 | 1875000 |  | VENTANAS I
0.3.1 |  |  | Disbursement #00 |  | 7950 | 0
0.4 |  |  | Disbursement #00 |  | 11250 | 0
0.6.2 |  |  | Disbursement #00 |  | 4800 | 0
0.6.3 |  |  | Disbursement #00 |  | 2400 | 0
0.7 |  |  | Disbursement #00 |  | 42375 | 0
0.8 |  |  | Disbursement #00 |  | 20000 | 0
0.9 |  |  | Disbursement #00 |  | 6000 | 0
0.9 |  |  | Disbursement #00 |  | 6480 | 0
2.1.1 |  |  | Disbursement #00 |  | 14500 | 0
3.1 |  |  | Disbursement #00 |  | 8236.005 | 0
3.3 |  |  | Disbursement #00 |  | 3779.624 | 0
3.4 |  |  | Disbursement #00 |  | 7342.175 | 0
4.4 |  |  | Disbursement #00 |  | 1695 | 0
5.1 |  |  | Disbursement #00 |  | 5000 | 0
5.2 |  |  | Disbursement #00 |  | 4972 | 0
5.6 |  |  | Disbursement #00 |  | 50000 | 0
6.2 |  |  | Disbursement #00 |  | 2500 | 0
6.3 |  |  | Disbursement #00 |  | 24085.9 | 0
0.1 |  |  | Disbursement #00 |  | 450000 | 450000
3.2 |  |  | Disbursement #01 - 06/05/2024 | Topography Lidar | 25000 | 25000
3.2 |  |  | Disbursement #01 - 06/05/2024 | Topography vat tax Pending | 3250 | 3250
0.0001 |  |  | Disbursement #01 - 06/05/2024 | Soil analysis | 10170 | 10170
0.0001 |  |  | Disbursement #01 - 06/05/2024 | Boundary Analysis and Marking | 5085 | 5085
0.0001 |  |  | Disbursement #01 - 06/05/2024 | Water testing | 1915.35 | 1915.35
0.0001 |  |  | Disbursement #01 - 06/05/2024 | Environmental Feasibility Report | 8737.16 | 8737.16
0.0001 |  |  | Disbursement #01 - 06/05/2024 | Tree Trimming $880+Vat per day | 4972 | 4972
0.3.1 |  |  | Disbursement #01 - 06/05/2024 | Constitution of 13 Corps | 0 | 0
0.3.1 |  |  | Disbursement #01 - 06/05/2024 | 13 Certifications for Muni Application | 983.1 | 983.1
0.3.1 |  |  | Disbursement #01 - 06/05/2024 | Constitution of 2 Corps | 2034 | 2034
0.2 |  |  | Disbursement #01 - 06/05/2024 | 2 Certifications for Muni Application | 151.25 | 151.25
0.0001 |  |  | Disbursement #01 - 06/05/2024 | Legal Fees (local Attorney plus Municipal and Environmental fees) | 25000 | 25000
0.0001 |  |  | Disbursement #02 - 07/08/2024 | Boundary Analysis and Marking | 5085 | 5085
0.0001 |  |  | Disbursement #02 - 07/08/2024 | Environmental Feasibility Report /Payment # 2 after inspections | 8737.16 | 8737.16
0.0001 |  |  | Disbursement #02 - 07/08/2024 | Tree Trimming $880+Vat per day | 5280 | 5280
0.0001 |  |  | Disbursement #02 - 07/08/2024 | Soil Studies | 24052.5 | 24052.5
0.3.1 |  |  | Disbursement #02 - 07/08/2024 | Constitution of 13 Corps | 0 | 0
0.2 |  |  | Disbursement #02 - 07/08/2024 | Surveyor (13 new land surveys for concession areas) | 18362.5 | 18362.5
0.2 |  |  | Disbursement #02 - 07/08/2024 | Concession files( Inspections and legal filing) | 25000 | 25000
0.3.1 |  |  | Disbursement #02 - 07/08/2024 | Legal Fees (New Corporations) | 3442 | 3442
0.5 |  |  | Helicopter Charter SJO-Venta-CWL | Helicopter Wire - 25/7/2024 | 18083 | 18083
3.2 |  |  | Disbursement #03 - 07/08/2024 | New Plano Registration for Ventanas (beach and hill) +Piñuelas Beach | 10452.5 | 10452.5
0.2 |  |  | Disbursement #03 - 07/08/2024 | Surveyors (13 new land surveys for concession areas) to complete 75% | 9181.25 | 9181.25
0.2 |  |  | Disbursement #03 - 07/08/2024 | Surveyor (2 new land surveys for concession areas) | 5650 | 5650
0.0001 |  |  | Disbursement #03 - 07/08/2024 | Soil Studies (to complete 75% after perforations and to get preliminar report) | 6645.89 | 6645.89
0.2 |  |  | Disbursement #03 - 07/08/2024 | Refund for Leandro and workers to chop property lines with Topographer | 800 | 800
0.0001 |  |  | Disbursement #03 - 07/08/2024 | Environmental Feasibility Report Final Installement to complete the 100% | 17474.32 | 17474.32
0.0001 |  |  | Disbursement #03 - 07/08/2024 | Tree Trimming $880+Vat per day Yedier Gustavo Gamboa Cerdas | 6160 | 6160
0.0001 |  |  | Disbursement #03 - 07/08/2024 | Trails Chopping $400+Vat per day Yedier Gustavo Gamboa Cerdas | 20000 | 20000
0.0001 |  |  | Disbursement #03 - 07/08/2024 | Mula supoort to access points for soil test ($50/day) until August 12th | 1100 | 1100
0.2 |  |  | Disbursement #03 - 07/08/2024 | Filing of "first Position in SINAC for Piñuelas Maritime Zone Usage" (legal fees,doc) | 2500 | 2500
0.3.1 |  |  | Disbursement #03 - 07/08/2024 | Corporate Structure - Reimbursement of Legal Costs | 13227 | 13227
0.3 |  |  | Payments out of ESCROW NOT REQUESTED IN THE DD LIST | PV2 Fact Exp 22 - Legal / Escrow Fees | 1965 | 1965
0.3 |  |  | Payments out of ESCROW NOT REQUESTED IN THE DD LIST | PV2 inv 1971-Inv1972 Legal expenses | 14351 | 14351
0.3 |  |  | Payments out of ESCROW NOT REQUESTED IN THE DD LIST | PV2 Inv03 BL Hovde Master Legal expenses | 3390 | 3390
0.3 |  |  | Payments out of ESCROW NOT REQUESTED IN THE DD LIST | Legal Fees Billed - PV2 FAC 2000 2001 P189 Alta Ba | 12093.75 | 12093.75
0.0001 |  |  | Disbursement #04 - 10/18/2024 | Soil Studies (final payment prior obtaining report) | 7212.07 | 7212.07
0.0001 |  |  | Disbursement #04 - 10/18/2024 | Soil Studies (Extra charge for difficult access to perforation points) 22 points | 5883.9 | 5883.9
0.2 |  |  | Disbursement #04 - 10/18/2024 | Surveyors (13 new land surveys for concession areas to complete 100% /Surveys were completed at filing ) | 9181.25 | 9181.25
0.2 |  |  | Disbursement #04 - 10/18/2024 | Surveyors (2 Tortuga new land surveys for concession areas to complete 100% /Surveys were completed at filing ) | 1250 | 1250
0.2 |  |  | Disbursement #04 - 10/18/2024 | Surveyors (13 new land surveys for concession areas) Adjusments after Muni/Minaet inspections | 9181.25 | 9181.25
0.2 |  |  | Disbursement #04 - 10/18/2024 | Surveyors (2 Tortuga new land surveys for concession areas) Adjusments after Muni/Minaet inspections | 1250 | 1250
0.0001 |  |  | Disbursement #04 - 10/18/2024 | Tree Trimming $880+Vat per day Yedier Gustavo Gamboa Cerdas | 20998.91 | 20998.91
0.0001 |  |  | Disbursement #04 - 10/18/2024 | Legal fees to file Concession areas Final Report to get concession areas and Patrimony areas | 15000 | 15000
0.0001 |  |  | Disbursement #04 - 10/18/2024 | Preliminary visit and requirements advisory for Patrimony (Eduardo) | 5000 | 5000
1.2 |  |  | Disbursement #05 - 16/12/2024 | Ventanas - Tree Trim Week Aug 1-2 | 5320 | 5320
0.0001 |  |  | Disbursement #05 - 16/12/2024 | Cinco Ventanas - Tree Trimming and Landscaping - Ventanas - Week #3 Aug | 300 | 300
0.0001 |  |  | Disbursement #05 - 16/12/2024 | Cinco Ventanas - Tree Trimming and Landscaping - Ventanas - Week #4 Aug | 300 | 300
0.0001 |  |  | Disbursement #05 - 16/12/2024 | Cinco Ventanas - Tree Trimming and Landscaping - Ventanas - Week #1 Sept | 300 | 300
0.0001 |  |  | Disbursement #05 - 16/12/2024 | Cinco Ventanas - Tree Trimming and Landscaping - Ventanas - Week #2-4 Sept | 1100 | 1100
0.0001 |  |  | Disbursement #05 - 16/12/2024 | Cinco Ventanas - Tree Trimming and Landscaping - Ventanas - Week #1-4 Oct | 2000 | 2000
1.2 |  |  | Disbursement #05 - 16/12/2024 | Trimming and Views - Week 1-3 Nov 2024 | 1500 | 1500
0.0001 |  |  | Disbursement #05 - 16/12/2024 | Ventanas - Reimbursement for Grass Chopping Venlanas | 265.81 | 265.81
0.6.1 |  |  | Disbursement #05 - 16/12/2024 | Days Worked - Grounds Maintenance Ventanas | 475.25 | 475.25
0.6.1 |  |  | Disbursement #05 - 16/12/2024 | Property Grounds Maintenance - Week of 11-09 - Ventanas | 352.59 | 352.59
0.6.1 |  |  | Disbursement #05 - 16/12/2024 | Grounds Main! Week 10-31 224 Ventanas | 343.25 | 343.25
0.6.1 |  |  | Disbursement #05 - 16/12/2024 | Grounds Mint Week 10-25 Ventanas | 555.56 | 555.56
0.6.1 |  |  | Disbursement #05 - 16/12/2024 | Week from 11/16 and 11/23 Alexis Ventanas (refundable exp.) | 990.02 | 990.02
0.6.1 |  |  | Disbursement #05 - 16/12/2024 | Grounds Maintenance - Ventanas Week 11-30 / 12-14 | 921.21 | 921.21
0.7 |  |  | Disbursement #05 - 16/12/2024 | Driveway and Pad Ventanas | 14200 | 14200
0.7 |  |  | Disbursement #05 - 16/12/2024 | Dev. Director Monthly Fee Nov 2024 | 14125 | 14125
0.7 |  |  | Disbursement #05 - 16/12/2024 | Dev. Director Monthly Fee Dec 2024 | 14125 | 14125
0.3 |  |  | Disbursement #05 - 16/12/2024 | Legal Fees Rendered Ventanas | 18712.8 | 18712.8
0.4 |  |  | Disbursement #05 - 16/12/2024 | Financial Controller 25% Salary -Ventanas | 2055 | 2055
0.4 |  |  | Disbursement #05 - 16/12/2024 | Admin Fee Budget | 1695 | 1695
0.7 |  |  | Disbursement #05 - 16/12/2024 | To be Sent to Miami - Waiting for Wiring Instructions | 18350 | 18350
0.7 |  |  | Disbursement #05 - 16/12/2024 | To be Sent to Miami - Bank fees for inU wire | 120 | 120
6.2 |  |  | Disbursement #06 - 01/13/2025 | Cinco Ventanas Lot Survey Easement | 2500 | 2500
6.3 |  |  | Disbursement #06 - 01/13/2025 | Driveway and Pad Final Payment | 9885.9 | 9885.9
3.1 |  |  | Disbursement #06 - 01/13/2025 | Ventanas DEHC Civil Engineer (Hydro/Discharge/MP Review) | 17967 | 17967
3.1 |  |  | Disbursement #06 - 01/13/2025 | Eduardo Patrimony / Forestry | 4972 | 4972
0.7 |  |  | Disbursement #06 - 01/13/2025 | Development Director Jan | 14125 | 14125
0.4 |  |  | Disbursement #06 - 01/13/2025 | Admin Fee Budget + Financial Controller 25% Salary | 3750 | 3750
0.4 |  |  | Disbursement #06 - 01/13/2025 | Farm Manager+ Worker | 1600 | 1600
0.4 |  |  | Disbursement #06 - 01/13/2025 | CCSS (Social Security) | 800 | 800
0.0001 |  |  | Disbursement #06 - 01/13/2025 | Pura Vida Drilling - Satellite Analysis | 1695 | 1695
1.3 |  |  | Disbursement #06 - 01/13/2025 | Open Paths to Private Beaches (Celina / Elefante) | 6480 | 6480
6.2 |  |  | Disbursement #06 - 01/13/2025 | Legal Fees | 7950 | 7950
0.911 |  |  | Disbursement #06 - 01/13/2025 | Gates | 6000 | 6000
0.6.4 |  |  | Disbursement #06 - 01/13/2025 | Property Maintenance | 20000 | 20000
0.7 |  |  | Disbursement #07 - 03/10/2026 | Development Director Feb 2025 | 14125 | 14125
0.4 |  |  | Disbursement #07 - 03/10/2026 | Admin Fee Budget + Financial Controller 25% Salary Feb 2025 | 3750 | 3750
0.4 |  |  | Disbursement #07 - 03/10/2026 | Farm Manager + Worker Feb 2025 | 1600 | 1600
0.4 |  |  | Disbursement #07 - 03/10/2026 | CCSS (Social Security) Feb 2025 | 800 | 800
1.4 |  |  | Disbursement #07 - 03/10/2026 | Water System 30% Downpayment of 155 000.00 $45 500.00 | 46500 | 46499.9965
0.7 |  |  | Disbursement #07 - 03/10/2026 | Legal Expenses - Land Use Concessions (ALTA BATALLA)} 50% | 7250 | 7250
0.9 |  |  | Disbursement #07 - 03/10/2026 | Ventanas Road to Piñuela Gustavo Gamboa - Refund | 1085 | 1085
0.7 |  |  | Disbursement #09 - 04/10/2025 | Development Director March 2025 | 14125 | 14125
0.4 |  |  | Disbursement #09 - 04/10/2025 | Admin Fee Budget + Financial Controller 25% Salary March 2025 | 3750 | 3750
0.6.1 |  |  | Disbursement #09 - 04/10/2025 | Farm Manager + Worker March 2025 | 1600 | 1600
0.6.1 |  |  | Disbursement #09 - 04/10/2025 | CCSS (Social Security) March 2025 | 800 | 800
2.1.2 |  |  | Disbursement #09 - 04/10/2025 | EDSA November Payment | 54131.6 | 54131.6
2.1.3 |  |  | Disbursement #09 - 04/10/2025 | EDSA November Payment | 7500 | 7500
6.3 |  |  | Disbursement #09 - 04/10/2025 | Water Meters (CINCO VENTANAS) | 556 | 556
6.3 |  |  | Disbursement #09 - 04/10/2025 | INTERNAL ROAD (CINCO VENTANAS) | 3000 | 3000
3.1 |  |  | Disbursement #09 - 04/10/2025 | FOREST Inventory | 2600 | 2600
0.3 |  |  | Disbursement #09 - 04/10/2025 | Certified Cash flow preparation for new bank accounts - Ventanas Holding | 282.5 | 282.5
0.9 |  |  | Disbursement #09 - 04/10/2025 | Chopping Road pinuelas elefante | 519.8 | 519.8
0.9 |  |  | Disbursement #09 - 04/10/2025 | Chopping pinuelas behind pool path | 169.5 | 159.5
0.9 |  |  | Disbursement #09 - 04/10/2025 | Chopping pinuelas road | 395.5 | 395.5
6.3 |  |  | Disbursement #09 - 04/10/2025 | Work with topographer | 141.25 | 141.25
0.7 |  |  | Disbursement #10 - 05/01/2025 | Development Director Abril 2025 | 14125 | 14125 |  | 14125
0.4 |  |  | Disbursement #10 - 05/01/2025 | Admin Fee Budget + Financial Controller 25% Salary Abril 2025 | 3750 | 3750 |  | 6150
0.6.1 |  |  | Disbursement #10 - 05/01/2025 | Farm Manager + Worker April 2025 | 1600 | 1600 |  | 6150
0.6.1 |  |  | Disbursement #10 - 05/01/2025 | CCSS (Social Security) April 2025 | 800 | 800 |  | 6150
6.3 |  |  | Disbursement #10 - 05/01/2025 | Internal Road (Cinco Ventanas) Materials | 4000 | 4000
0.5 |  |  | Disbursement #10 - 05/01/2025 | Owners expenses pay back to CWL | 14851.54 | 14851.54
0.911 |  |  | Disbursement #10 - 05/01/2025 | Construction Works in Piñuela – Gates | 1400 | 1400
3.1 |  |  | Disbursement #10 - 05/01/2025 | Forest stratification technical analysis. | 3390 | 3390
0.7 |  |  | Disbursement #11 - 06/01/2025 | Development Director MAY 2025 | 14125 | 14125 |  | 14125
0.4 |  |  | Disbursement #11 - 06/01/2025 | Admin Fee Budget + Financial Controller 25% Salary MAY 2025 | 3750 | 3750 |  | 6150
0.6.1 |  |  | Disbursement #11 - 06/01/2025 | Farm Manager + Worker MAY 2025 | 1600 | 1600 |  | 6150
0.6.1 |  |  | Disbursement #11 - 06/01/2025 | CCSS (Social Security) MAY 2025 | 800 | 800 |  | 6150
3.1 |  |  | Disbursement #11 - 06/01/2025 | YEDIER GUSTAVO GAMBOA CERDAS | 380 | 380 |  | 380
3.1 |  |  | Disbursement #11 - 06/01/2025 | YEDIER GUSTAVO GAMBOA CERDAS | 1130 | 1130 |  | 1130
0.6.4 |  |  | Disbursement #11 - 06/01/2025 | ALTA BATALLA | 30 | 30 |  | 5002
0.6.4 |  |  | Disbursement #11 - 06/01/2025 | ALTA BATALLA | 1017 | 1017 |  | 5002
0.6.4 |  |  | Disbursement #11 - 06/01/2025 | ALTA BATALLA | 3955 | 3955 |  | 5002
0.5 |  |  | Disbursement #11 - 06/01/2025 | NACASCOLO AIR (SJO TO VENTANAS) | 4620 | 4620 |  | 7467.61
0.5 |  |  | Disbursement #11 - 06/01/2025 | NACASCOLO AIR (QUEPOS TO SJO) | 2847.6 | 2847.6 |  | 7467.61
0.5 |  |  | Disbursement #11 - 06/01/2025 | OXIGEN JUNGLE VILLAS | 3101.85 | 3101.85 |  | 3101.85
5.8 |  |  | Disbursement #11 - 06/01/2025 | Topography Services | 15000 | 0
5.8 |  |  | Disbursement #11 - 06/01/2025 | Legal: Concessions and Muncipality Meetings | 7500 | 0
0.7 |  |  | Disbursement #12 - 07/01/2025 | Development Director JUNE 2025 | 14125 | 14125 |  | 14125
0.4 |  |  | Disbursement #12 - 07/01/2025 | Admin Fee Budget + Financial Controller 25% Salary JUNE 2025 | 3750 | 3750 |  | 6150
0.4 |  |  | Disbursement #12 - 07/01/2025 | Farm Manager + Worker JUNE 2025 | 1600 | 1600 |  | 6150
0.4 |  |  | Disbursement #12 - 07/01/2025 | CCSS (Social Security) JUNE 2025 | 800 | 800 |  | 6150
1.4 |  |  | Disbursement #12 - 07/01/2025 | Water System 70% Downpayment of 155 000.00 ($109500) PAID $46500 | 109500 | 109500
0.5 |  |  | Disbursement #12 - 07/01/2025 | Invoice from Oxigen for Meals | 137.39 | 137.39 |  | 137.39
3.1 |  |  | Disbursement #12 - 07/01/2025 | Treeming for view Ventanas with Blake and Karol | 1130 | 1130 |  | 1130
3.1 |  |  | Disbursement #12 - 07/01/2025 | Pura Selva clearing the area for the gaviones | 380 | 380 |  | 380
3.1 |  |  | Disbursement #12 - 07/01/2025 | Shey Coordinated | 2576 | 2576 |  | 2576
1.4 |  |  | Disbursement #12 - 07/01/2025 | PIPELINE CROSSING CONSTRUCTION PROJECT – PLAYA VENTANAS $14880+IVA | 16814.4 | 16814.4
0.7 |  |  | Disbursement #13 - 08/01/2025 | Development Director August 2025 | 14125 | 14125 |  | 14125
0.4 |  |  | Disbursement #13 - 08/01/2025 | Admin Fee Budget + Financial Controller 25% Salary AUGUST 2025 | 3750 | 3750 |  | 6150
0.6.1 |  |  | Disbursement #13 - 08/01/2025 | Farm Manager + Worker AUGUST 2025 | 1600 | 1600 |  | 6150
0.6.1 |  |  | Disbursement #13 - 08/01/2025 | CCSS (Social Security) AUGUST 2025 | 800 | 800 |  | 6150
6.3 |  |  | Disbursement #13 - 08/01/2025 | Entrance Pura Selva -5 VENTANAS (Total $5694.00 Minus $5400 Previous wired) | 294 | 0
3.1 |  |  | Disbursement #13 - 08/01/2025 | Environmental Forestry Study-ALTA BATALLA (Permitting process) | 4350.5 | 4350.5 |  | 4350.5
0.7 |  |  | Disbursement #14 - 09/01/2025 | Development Director SEPTEMBER 2025 | 14125 | 14125 |  | 14125
0.4 |  |  | Disbursement #14 - 09/01/2025 | Admin Fee Budget + Financial Controller 25% Salary SEPTEMBER 2025 | 3750 | 3750 |  | 6150
0.6.1 |  |  | Disbursement #14 - 09/01/2025 | Farm Manager + Worker SEPTEMBER 2025 | 1600 | 1600 |  | 6150
0.6.1 |  |  | Disbursement #14 - 09/01/2025 | CCSS (Social Security) SEPTEMBER 2025 | 800 | 800 |  | 6150
0.6.2 |  |  | Disbursement #14 - 09/01/2025 | Alex Payment- Care Taker Ventanas | 1120 | 1120
1.4 |  |  | Disbursement #14 - 09/01/2025 | Final payment + extra drilling under highway + water meters | 32500 | 32500
0.7 |  |  | Disbursement #15 - 10/01/2025 | Development Director OCTOBER 2025 | 14125 | 14125 |  | 14125
0.4 |  |  | Disbursement #15 - 10/01/2025 | Admin Fee Budget + Financial Controller 25% Salary OCTOBER 2025 | 3750 | 3750 |  | 6150
0.6.1 |  |  | Disbursement #15 - 10/01/2025 | Farm Manager + Worker OCTOBER 2025 | 1600 | 1600 |  | 6150
0.6.1 |  |  | Disbursement #15 - 10/01/2025 | CCSS (Social Security) OCTOBER 2025 | 800 | 800 |  | 6150
0.6.2 |  |  | Disbursement #15 - 10/01/2025 | Alex Payment- Care Taker Ventanas | 1000 | 0
3.1 |  |  | Disbursement #15 - 10/01/2025 | DEHC for road alignment $2385.00 plus IVA | 2695.05 | 2695.05 |  | 3359.5
3.1 |  |  | Disbursement #15 - 10/01/2025 | CASTRO & DE LA TORRE: Soil Studies IVA | 312.246 | 0
3.1 |  |  | Disbursement #15 - 10/01/2025 | FOREST INSPECTION $1585.00 plus IVA | 1791.05 | 0
0.7 |  |  | Disbursement #16 - 11/01/2025 | Development Director NOVEMBER 2025 | 14125 | 14125 |  | 14125
0.4 |  |  | Disbursement #16 - 11/01/2025 | Admin Fee Budget + Financial Controller 25% Salary NOVEMBER 2025 | 3750 | 3750 |  | 3750
0.6.1 |  |  | Disbursement #16 - 11/01/2025 | Farm Manager + Worker NOVEMBER 2025 | 1600 | 1600 |  | 1600
0.6.1 |  |  | Disbursement #16 - 11/01/2025 | CCSS (Social Security) NOVEMBER 2025 | 800 | 800 |  | 800
0.6.2 |  |  | Disbursement #16 - 11/01/2025 | Alex Payment- Care Taker Ventanas | 1824.705 | 1824.705 |  | 1824.705
3.1 |  |  | Disbursement #16 - 11/01/2025 | DEHC for road alignment Pending Previous Request $4255 +IVA | 4808.15 | 4808.15 |  | 3943.7
3.1 |  |  | Disbursement #16 - 11/01/2025 | CASTRO & DE LA TORRE: Soil Studies + IVA | 312.246 | 0
3.1 |  |  | Disbursement #16 - 11/01/2025 | SEED: Developer Milestone accomplishment for water certification for access and system acceptance: $25,000 + VAT | 28250 | 28250 |  | 28249.999999999996
3.1 |  |  | Disbursement #16 - 11/01/2025 | Ojachal Garderns. Permit Engineer, Forestry Engineer, Land Surveyor DEHC Stay C Stay Aug 11, 2025 | 813.6 | 813.6
3.1 |  |  | Disbursement #16 - 11/01/2025 | Ojachal Garderns. Permit Engineer, Forestry Engineer, Land Surveyor DEHC Stay Stay Aug 26, 2025 | 310.64 | 310.64
3.1 |  |  | Disbursement #16 - 11/01/2025 | Ojachal Garderns. Permit Engineer, Forestry Engineer, Land Surveyor DEHC Stay Stay Oct 14-15, 2025 | 542.4 | 542.4
3.1 |  |  | Disbursement #16 - 11/01/2025 | ALTA BATALLA: Annual Fee Ventanas Administration Trust | 3616 | 3616
0.6.4 |  |  | Disbursement #16 - 11/01/2025 | Ferreteria Palmares: Materiales | 1003.9 | 0
1.4 |  |  | Disbursement #16 - 11/01/2025 | Water Meters ASADA | 555 | 0
1.4 |  |  | Disbursement #16 - 11/01/2025 | Water Consumption for September and October 2025 Ventanas Meters | 103.9 | 132.92
0.7 |  |  | Disbursement #18 - 12/01/2025 | Development Team - DECEMBER 2025 | 14125 | 14125
0.4 |  |  | Disbursement #18 - 12/01/2025 | Admin Fee Budget + Financial Controller 25% Salary - DECEMBER 2025 | 3750 | 3750
0.4 |  |  | Disbursement #18 - 12/01/2025 | CCSS (Social Security) DECEMBER 2025 | 800 | 800
0.6.2 |  |  | Disbursement #18 - 12/01/2025 | Alexi Payment- Care Taker Ventanas | 1824.705 | 1824.705
0.6.4 |  |  | Disbursement #18 - 12/01/2025 | CONSTRUPLAZA, SA. Property landscape Maintenace equipment | 491.08 | 0
3.1 |  |  | Disbursement #18 - 12/01/2025 | Forestry Engineer - Survey for forestry study - $2385+VAT | 2695.05 | 0
3.1 |  |  | Disbursement #18 - 12/01/2025 | Environmental Regent. Preliminary Environmental Study D1 | 5830.8 | 0
3.1 |  |  | Disbursement #18 - 12/01/2025 | DEHC Earth Movement Civil Engineering Services 73HA | 12373.5 | 12373.5
3.1 |  |  | Disbursement #18 - 12/01/2025 | DEHC Full engineering design of phase one for Civil and MEP to develop the condo infrastructure. | 16385 | 16385
3.1 |  |  | Disbursement #18 - 12/01/2025 | DEHC Civil Engineer and Permit Engineer - the start of the condo permits. | 5424 | 3336.33
3.1 |  |  | Disbursement #18 - 12/01/2025 | Permit - MOPT highway department | 1356 | 0
3.1 |  |  | Disbursement #18 - 12/01/2025 | Certifications for various DD items ALTA BATALLA | 40 | 40
3.1 |  |  | Disbursement #18 - 12/01/2025 | Annual housekeeping of the ventanas corporations. Due in November yearly-ALTA BATALLA | 19000.8 | 19000.8
3.1 |  |  | Disbursement #18 - 12/01/2025 | Due diligence Piñuelas charge for Hovde Master ALTA BATALLA | 9865 | 9865
0.7 |  |  | Disbursement #19 - 01/01/2026 | Development Team - JANUARY 2026 | 14125 | 14125
0.4 |  |  | Disbursement #19 - 01/01/2026 | Admin Fee Budget + Financial Controller 25% Salary - JANUARY 2026 | 3750 | 3750
0.4 |  |  | Disbursement #19 - 01/01/2026 | CCSS (Social Security) JANUARY 2026 | 800 | 800
0.6.2 |  |  | Disbursement #19 - 01/01/2026 | Alexi Payment- Care Taker Ventanas | 1824.705 | 1824.705
3.1 |  |  | Disbursement #19 - 01/01/2026 | Certifications for various DD items ALTA BATALLA | 715.25 | 715.25
3.4 |  |  | Disbursement #19 - 01/01/2026 | Due diligence Piñuelas charge for Hovde Master ALTA BATALLA | 74 | 74
9.1.1 |  |  | Disbursement #19 - 01/01/2026 | Phase 1/2/3 Pre Consultations $6500 +IVA DEHC | 7345 | 7345
9.1.2 |  |  | Disbursement #19 - 01/01/2026 | Phase 1/2/3 Discharge permit MOPT and Municipality $1800 + IVA DEHC | 2034 | 2034
9.1.3 |  |  | Disbursement #19 - 01/01/2026 | Phase 1 Permit (Includes topo of the existing road) $14500 +IVA DEHC | 16385 | 16385
0.6.4 |  |  | Disbursement #19 - 01/01/2026 | Materiales Ferreteria Construmas | 1016.4 | 1041.39
0.7 |  |  | Disbursement #20 - 02/01/2026 | Development Team - FEBRUARY 2026 | 14125 | 14125
0.4 |  |  | Disbursement #20 - 02/01/2026 | Admin Fee Budget + Financial Controller 25% Salary - FEBRUARY 2026 | 3750 | 3750
0.4 |  |  | Disbursement #20 - 02/01/2026 | CCSS (Social Security) FEBRUARY 2026 | 800 | 800
0.6.2 |  |  | Disbursement #20 - 02/01/2026 | Alexi Payment- Care Taker Ventanas | 1824.705 | 1824.705
0.911 |  |  | Disbursement #20 - 02/01/2026 | Fence Installation-Gustavo $880.01 IVI | 880.01 | 880.01
0.1.2 |  |  | Disbursement #20 - 02/01/2026 | Titled Property Annual Taxes | 37500 | 0
0.1.3 |  |  | Disbursement #20 - 02/01/2026 | Holding Corporation Taxes | 6300 | 6233.63
0.9 |  |  | Disbursement #20 - 02/01/2026 | Fallen Trees / Cutting Grass | 2000 | 0
0.7 |  |  | Disbursement #21 - 03/01/2026 | Development Team - MARCH 2026 | 14125 | 14125
0.4 |  |  | Disbursement #21 - 03/01/2026 | Admin Fee Budget + Financial Controller 25% Salary - MARCH 2026 | 3750 | 3750
0.4 |  |  | Disbursement #21 - 03/01/2026 | CCSS (Social Security) MARCH 2026 | 800 | 800
0.6.2 |  |  | Disbursement #21 - 03/01/2026 | Alexi Payment- Care Taker Ventanas | 1824.705 | 1824.705
0.9 |  |  | Disbursement #21 - 03/01/2026 | Road Design Project – Accommodation Charges for 5 Engineers (4 Nights) – MOPT | 2335.61 | 0
3.2 |  |  | Disbursement #21 - 03/01/2026 | Certifications for various DD items ALTA BATALLA | 443.02 | 0
0.7 |  |  | Disbursement #22 - 04/01/2026 | Development Team - APRIL 2026 | 14125 | 14125
0.4 |  |  | Disbursement #22 - 04/01/2026 | Admin Fee Budget + Financial Controller 25% Salary - APRIL 2026 | 3750 | 3750
0.4 |  |  | Disbursement #22 - 04/01/2026 | CCSS (Social Security) APRIL 2026 | 800 | 800
0.6.2 |  |  | Disbursement #22 - 04/01/2026 | Alexi Payment- Care Taker Ventanas | 1824.705 | 1824.705
3.4 |  |  | Disbursement #22 - 04/01/2026 | Second payment of two at the end of the Master plan analysis and condominium strategy $11500*50% DEHG +IVA | 6497.5 | 0
3.5.1 |  |  | Disbursement #22 - 04/01/2026 | First payment of three when starting the schematic design: $103,600 *30% DEHG + IVA | 35120.4 | 35120.4
Unrecorded Center |  |  |  |  | 0 | 0
Estimates & Quotes |  |  |  |  | 0 | 0
Service Done/Not Posted to Sage |  |  |  |  | 0 | 0

## Timeline Detail
Project Category | Phase | WBS NUMBER | Task Title | Budget Revised | YTD Expense | Remaining | Forecast
0.0001
0.0002
2.1.1
2.1.2
2.1.3
2.1.4
2.2
9.1.1
9.1.2
9.1.3
9.2.1
9.3.1
7.2
7.3
7.4
7.5
7.6
7.7
5.1
5.2
5.3
5.4
5.5
5.6
5.7
5.8
8.3
0.1
0.1.1
0.1.2
0.1.3
0.2
0.3
0.3.1
0.4
0.5
0.6.1
0.6.2
0.6.3
0.6.4
0.6.5
0.7
0.8
0.9
0.911
1.1
1.2
1.3
1.4
6.1
6.2
6.3
6.4
6
3.1
3.2
3.3
3.4
3.5
3.5.1
3.52
3.6
3.7
3.8
3.9
3.101
3.11
4.1
4.2.1
4.2.2
4.2.3
4.3
4.4
8.1
8.2
8.4
7.1

## Job Cost Report
DASHBOARD VENTANAS — Job Cost Report
Modelo vivo. Editá el LEDGER y todo recalcula.
[13 empty] | Q1 2026 | Q1 2026 | Q1 2026 | Q1 2026 | Q1 2026 | Q1 2026 | Q1 2026 | Q1 2026 | Q1 2026 | Q1 2026 | Q1 2026 | Q1 2026 | Q1 2026 | Q1 2026 | Q1 2026 | Q1 2026 | Q1 2026 | Q2 2026 | Q2 2026 | Q2 2026 | Q2 2026 | Q2 2026 | Q2 2026 | Q2 2026 | Q2 2026 | Q2 2026 | Q2 2026 | Q2 2026 | Q2 2026 | Q2 2026 | Q2 2026 | Q2 2026 | Q2 2026 | Q2 2026 | Q3 2026 | Q3 2026 | Q3 2026 | Q3 2026 | Q3 2026 | Q3 2026 | Q3 2026 | Q3 2026 | Q3 2026 | Q3 2026 | Q3 2026 | Q3 2026 | Q3 2026 | Q3 2026 | Q3 2026 | Q3 2026 | Q3 2026 | Q4 2026 | Q4 2026 | Q4 2026 | Q4 2026 | Q4 2026 | Q4 2026 | Q4 2026 | Q4 2026 | Q4 2026 | Q4 2026 | Q4 2026 | Q4 2026 | Q4 2026 | Q4 2026 | Q4 2026 | Q4 2026 | Q4 2026
[13 empty] | JAN 2026 | JAN 2026 | JAN 2026 | JAN 2026 | MES | FEB 2026 | FEB 2026 | FEB 2026 | FEB 2026 | MES | MAR 2026 | MAR 2026 | MAR 2026 | MAR 2026 | MAR 2026 | MES | TRIMESTRE | APR 2026 | APR 2026 | APR 2026 | APR 2026 | MES | MAY 2026 | MAY 2026 | MAY 2026 | MAY 2026 | MES | JUN 2026 | JUN 2026 | JUN 2026 | JUN 2026 | JUN 2026 | MES | TRIMESTRE | JUL 2026 | JUL 2026 | JUL 2026 | JUL 2026 | MES | AUG 2026 | AUG 2026 | AUG 2026 | AUG 2026 | AUG 2026 | MES | SEP 2026 | SEP 2026 | SEP 2026 | SEP 2026 | MES | TRIMESTRE | OCT 2026 | OCT 2026 | OCT 2026 | OCT 2026 | MES | NOV 2026 | NOV 2026 | NOV 2026 | NOV 2026 | NOV 2026 | MES | DEC 2026 | DEC 2026 | DEC 2026 | DEC 2026 | MES | TRIMESTRE
Status | WBS | Task Title | Owner | Category | Phase | Budget Original | Budget Change | Budget Revised | Spend | Remaining | Forecast | Variance | 5 | 12 | 19 | 26 | JAN | 2 | 9 | 16 | 23 | FEB | 2 | 9 | 16 | 23 | 30 | MAR | Q1 2026 | 6 | 13 | 20 | 27 | APR | 4 | 11 | 18 | 25 | MAY | 1 | 8 | 15 | 22 | 29 | JUN | Q2 2026 | 6 | 13 | 20 | 27 | JUL | 3 | 10 | 17 | 24 | 31 | AUG | 7 | 14 | 21 | 28 | SEP | Q3 2026 | 5 | 12 | 19 | 26 | OCT | 2 | 9 | 16 | 23 | 30 | NOV | 7 | 14 | 21 | 28 | DEC | Q4 2026 | TOTAL
TOTAL <object object at 0x7f16e877ac70>
0-PROPERTY ACQUISITION
Completed | 0.0001 | Due Diligence / Closing Costs | HOVDE | 0-Property Acquisition | Phase 1 | 388000 | 415720.07
In process | 0.0002 | Property Acquisition | Partnership | 0-Property Acquisition | Phase 1 | 11250000 | 0 | [53 empty] | 1875000
TOTAL 0-Property Acquisition
CFIA CONDO
In process | 2.1.1 | Pre Workshop | EDSA | CFIA Condo | DESIGN | 14500 | 0 | [22 empty] | 14500
Approved | 2.1.2 | Workshop | EDSA | CFIA Condo | DESIGN | 24500 | 29631.6
Approved | 2.1.3 | Post Workshop / Conceptual Enlargements | EDSA | CFIA Condo | DESIGN | 48500 | 0 | [32 empty] | 41000
Approved | 2.1.4 | Travel Expenses MP | EDSA | CFIA Condo | DESIGN | 5000 | 0 | [44 empty] | 5000
Approved | 2.2 | Schematic Design | EDSA | CFIA Condo | DESIGN | 100000 | 0 | [50 empty] | 25000 | 25000 | 25000 | 25000
TOTAL CFIA Condo
CFIA INFRASTRUCTURE
In process | 9.1.1 | Phase 1/2/3 Pre Consultations | DEHC | CFIA Infrastructure | Phase 1 | 0 | 5424 | [10 empty] | -1921
In process | 9.1.2 | Phase 1/2/3 Discharge permit MOPT and Municipality | DEHC | CFIA Infrastructure | Phase 2 | 0 | 1356 | [10 empty] | -678
Approved | 9.1.3 | Phase 1 Permit (Includes topo of the existing road) | DEHC | CFIA Infrastructure | Phase 1 | 0 | 16385
Approved | 9.2.1 | Phase 2 Permit | DEHC | CFIA Infrastructure | Phase 2 | 0 | 8814 | [18 empty] | 8814
Approved | 9.3.1 | Phase 3 Permit | DEHC | CFIA Infrastructure | Phase 3 | 0 | 1356 | [18 empty] | 1356
Approved | 7.2 | Plan and approval of the two condominiums | Blake | CFIA Infrastructure | Phase 3 | 0 | 0
Approved | 7.3 | Cadastre Plan (only when we want to convey) | Surveyor | CFIA Infrastructure | Phase 3 | 102162.45 | 0 | [27 empty] | 51081.22 | [22 empty] | 51081.22
Approved | 7.4 | CFIA (1%) - Whole Project | Blake | CFIA Infrastructure | Phase 3 | 265000 | 0 | [44 empty] | 265000
Approved | 7.5 | INS (1.298%) - Phase Only | Blake | CFIA Infrastructure | Phase 3 | 129800 | 0 | [64 empty] | 129800
Approved | 7.6 | SETENA Bond (1.5% Value) - Phase Only | Partnership | CFIA Infrastructure | Phase 3 | 300000 | 0 | [61 empty] | 300000
Approved | 7.7 | Municipality (1%) - Phase Only | Permit Engineer | CFIA Infrastructure | Phase 3 | 100000 | 0 | [67 empty] | 100000
TOTAL CFIA Infrastructure
CONCESSIONS
In process | 5.1 | Preliminar Study for PNE applications in ACOSA, SINAC, and Muni | Eduardo | Concessions | SETENA Regional Review | 0 | 5000 | [56 empty] | 5000
In process | 5.2 | Engineering diagnosis to apply reversion of Patrimony areas to Muni ( to apply later for concessions ) | Eduardo consultant | Concessions | SETENA Regional Review | 9944 | 0 | [18 empty] | 4972 | [37 empty] | 4972
Approved | 5.3 | Application/ project description for PNE MINAET | Eduardo | Concessions | SETENA Regional Review | 15876.5 | 0 | [27 empty] | 15876.5
Approved | 5.4 | Survey new plans - Adjust to Government Regs | Surveyor | Concessions | SETENA Regional Review | 72207 | 0 | [25 empty] | 16950 | [6 empty] | 30000 | [6 empty] | 16950 |  |  | 8307
Approved | 5.5 | Create Draft Plans for Development | Randall | Concessions | SETENA Regional Review | 30000 | 0 | [32 empty] | 15000 | [8 empty] | 15000
In process | 5.6 | Legal Expenses - Concession MUNI | Herbet | Concessions | SETENA Regional Review | 100000 | 0 | [61 empty] | 100000
Approved | 5.7 | Legal Expenses - Land Use SINAC | Eduardo | Concessions | SETENA Regional Review | 50000 | 0 | [30 empty] | 20000 | [11 empty] | 20000 | [10 empty] | 10000
In process | 5.8 | Legal Expenses - Land Use Concessions (ALTA BATALLA)} | Roberto | Concessions | SETENA Regional Review | 14500 | 0 | [32 empty] | 7250 | [23 empty] | 7250
Approved | 8.3 | Finalize Creation of Concessions | Blake | Concessions |  | 42375 | 0 | [70 empty] | 42375
TOTAL Concessions
OVERHEAD
Approved | 0.1 | Property Interest | Partnership | Overhead | Phase 2 | 787500 | 0 | [53 empty] | 337500
Approved | 0.1.1 | Insurance | Partnership | Overhead | Phase 2 | 20000 | 0 | [53 empty] | 20000
Attention | 0.1.2 | Titled Property Annual Taxes | Partnership | Overhead | Phase 2 | 75000 | 0 | [13 empty] | 37500 | [39 empty] | 37500
Attention | 0.1.3 | Holding Corporation Taxes | Partnership | Overhead | Phase 2 | 12600 | 0 | [13 empty] | 6300 | [39 empty] | 6300
Approved | 0.2 | Concession/Land Use Leases | Partnership | Overhead | Phase 2 | 87000 | 0 | [30 empty] | 4492.5
Attention | 0.3 | Escrow and Legal Fees | Sergio Amador | Overhead | Phase 2 | 40000 | 10795.05
Attention | 0.3.1 | Corporation Management | Sergio Amador | Overhead | Phase 2 | 15000 | 4686.1
Attention | 0.4 | Admin Fee Budget + Financial Controller 25% Salary | Partnership | Overhead | Phase 2 | 86250 | 7500 | [8 empty] | 3750 |  |  |  |  | 3750 |  |  |  |  | 3750 | [6 empty] | 3750 |  |  |  |  | 3750 |  |  |  |  | 3750 | [6 empty] | 3750 |  |  |  |  | 3750 | [5 empty] | 3250 | [5 empty] | 3750 |  |  |  |  | 3750 | [5 empty] | 3750
Approved | 0.5 | Travel Expenses / Ownership | Partnership | Overhead | Phase 2 | 24000 | 19641.38
Attention | 0.6.1 | Farm Manager | Alexis | Overhead | Phase 2 | 23000 | 19334.4 | [8 empty] | 1824.71 |  |  |  |  | 1824.71 |  |  |  |  | 1824.71 | [6 empty] | 1824.71 |  |  |  |  | 1824.71 |  |  |  |  | 1824.71 | [6 empty] | 1824.71 |  |  |  |  | 1824.71 | [5 empty] | 1824.71 | [5 empty] | 1824.71 |  |  |  |  | 1824.71 | [5 empty] | 1824.71
Attention | 0.6.2 | Farm Worker | TBD | Overhead | Phase 2 | 13800 | 2569.41 | [8 empty] | 1000 |  |  |  |  | 1000 |  |  |  |  | 1000 | [6 empty] | 1000 |  |  |  |  | 1000 |  |  |  |  | 1000 | [6 empty] | 1000 |  |  |  |  | 600 | [5 empty] | 1000 | [5 empty] | 1000 |  |  |  |  | 1000 | [5 empty] | 1000
Attention | 0.6.3 | CCSS Employee Benefits |  | Overhead | Phase 2 | 18400 | 0 | [8 empty] | 1392.36 |  |  |  |  | 1412.36 |  |  |  |  | 1412.36 | [6 empty] | 1412.36 |  |  |  |  | 1412.36 |  |  |  |  | 1412.36 | [6 empty] | 1412.36 |  |  |  |  | 1212.36 | [5 empty] | 1412.36 | [5 empty] | 1412.36 |  |  |  |  | 1412.36 |  |  |  |  | 1671.74 | 1412.36
Approved | 0.6.4 | Main. Equip. / Expendables / Truck / Mula | Blake | Overhead | Phase 2 | 62500 | 0 | [27 empty] | 2500 | 29998 | [6 empty] | 2500 | [17 empty] | 2500
Approved | 0.6.5 | Procore (If we want to implement is system) | Blake | Overhead | Phase 2 | 21000 | 0 | [28 empty] | 13000 | [41 empty] | 8000
Attention | 0.7 | Development Director | Blake | Overhead | Phase 2 | 324875 | 68170 | [8 empty] | 14125 |  |  |  |  | 14125 |  |  |  |  | 14125 | [6 empty] | 14125 |  |  |  |  | 14125 |  |  |  |  | 14125 | [6 empty] | 14125 |  |  |  |  | 14125 | [5 empty] | 14125 | [5 empty] | 14125 |  |  |  |  | 14125 | [5 empty] | 14125
In process | 0.8 | Road Repairs | FyF | Overhead | Phase 2 | 30000 | 0 | [22 empty] | 30000
Approved | 0.9 | Fallen Trees / Cutting Grass | Alexis/Gustavo | Overhead | Phase 2 | 16000 | 24000 | [13 empty] | 2000 | [16 empty] | 2000 | [16 empty] | 2000 | [8 empty] | 31840.2
In process | 0.911 | Property Gates | Blake | Overhead | Phase 2 | 6000 | 1400
Attention | 1.1 | Gravel Existing Roads | FyF | Overhead | Phase 3 | 80000 | 0 | [30 empty] | 40000 |  |  |  |  | 40000
Approved | 1.2 | Opening Views | Tree Man Co. | Overhead | Phase 3 | 52800 | 0 | [30 empty] | 28380 | [19 empty] | 4400 | 4400 | 4400 | 4400
Attention | 1.3 | Opening Paths to Important Areas | Alexis | Overhead | Phase 3 | 6480 | 0
Attention | 1.4 | Water System | Blake | Overhead | Phase 3 | 155000 | 50314.4
Approved | 6.1 | Trim Trees to See View | Tree Man Co. | Overhead | PROPERTY | 7500 | 0 | [22 empty] | 7500
Approved | 6.2 | Survey Water Easement and Register | Marvin | Overhead | PROPERTY | 7500 | 5450 | [39 empty] | 2500
Approved | 6.3 | Cut Driveway and Building Pad + Gravel + Culverts | Sibaja | Overhead | PROPERTY | 20000 | 20000 | [56 empty] | 22416.85
Approved | 6.4 | Closing Costs | Karol | Overhead | PROPERTY | 48000 | 0 | [15 empty] | 48000
| 6 | Property Sale | Karol | Overhead | PROPERTY | -480000 | 0 | [15 empty] | -480000
TOTAL Overhead
SETENA D1
In process | 3.1 | Preliminary environmental study, D1 form | DEHC | Setena D1 | STUDIES | 14577 | 130000 | [39 empty] | 35759.86
Approved | 3.2 | Register Plans with Master Plan Roads | Surveyor | Setena D1 | ENGINEERING | 8000 | 30702.5
In process | 3.3 | Hydrological study / Discharge Permit | DEHC | Setena D1 | STUDIES | 8362 | 0 | [67 empty] | 8362
In process | 3.4 | Master plan analysis and condominium strategy | DEHC | Setena D1 | ENGINEERING | 12995 | 0 | [27 empty] | 6497.5 |  |  |  |  | 6497.5
Approved | 3.5 | Civil Engineering |  | Setena D1 | ENGINEERING | 0 | 0
Approved | 3.5.1 | - Schematic design | DEHC | Setena D1 | ENGINEERING | 117068 | 0 | [27 empty] | 20120 | 0.4 | 46827.2
Approved | 3.52 | - Construction drawings & quantities | DEHC | Setena D1 | ENGINEERING | 0 | 0
Approved | 3.6 | SETENA review | Government | Setena D1 | ENGINEERING | 0 | 0
Approved | 3.7 | Annexed information / Answer Questions | DEHC / Blake | Setena D1 | ENGINEERING | 0 | 0
Approved | 3.8 | SETENA Final review | Blake | Setena D1 | GOV | 0 | 0
Approved | 3.9 | SETENA (VA) Approval | DEHC / Blake | Setena D1 | ENGINEERING | 1457.7 | 0 | [62 empty] | 1457.7
Approved | 3.101 | Treatment Plant | Treatment Plant Eng. | Setena D1 | GOV | 50000 | 0 | [65 empty] | 25000 |  | 25000
Approved | 3.11 | Superficial infiltration test | Complete | Setena D1 | GOV | 0 | 0
Approved | 4.1 | Water Source Strategy | Blake | Setena D1 | WATER | 0 | 0
Approved | 4.2.1 | Water Department Negotiations | Blake | Setena D1 | WATER | 0 | 0
Approved | 4.2.2 | Water Department Installation (We pay and Donate) | Sierra | Setena D1 | WATER | 50000 | 0 | [30 empty] | 25000 |  |  |  |  | 25000
Approved | 4.2.3 | Water Department System Installation | Aguatech | Setena D1 | WATER | 150000 | 0
Approved | 4.3 | Spring Concession (Based on Strategy) | Blake | Setena D1 | WATER | 0 | 0
In process | 4.4 | Deep Well Concession / Casing x 2 Wells | PV Drilling | Setena D1 | WATER | 126227 | 0
Approved | 8.1 | Water Department Negotiations | Blake | Setena D1 | Phase 1 | 28250 | 0 | [32 empty] | 28250
Approved | 8.2 | SETENA (VA) Approval | Blake | Setena D1 | Phase 1 | 42375 | 0 | [70 empty] | 42375
Approved | 8.4 | Obtain Beach Club Permits | Blake | Setena D1 | BEACH CLUB P1 | 14125 | 0 | [50 empty] | 14125
TOTAL Setena D1
SIN CATEGORÍA
Approved | 7.1 | Project information | Blake | Sin categoría |  | 0 | 0
TOTAL Sin categoría
PROJECT TOTAL

## Leyenda
Leyenda de estados
| Not Started | not_started
| In process | in_process
| Approved | approved
| Attention | attention
| Completed | completed
Cómo colapsar
Los botones 1 · 2 · 3 arriba a la izquierda de la hoja Job Cost Report:
1 → sólo trimestres
2 → trimestres + meses
3 → todo el detalle semanal
También sirven los +/− sobre cada grupo de columnas.
Este archivo es un modelo VIVO: las columnas Spend, Remaining,
Forecast, los subtotales y los totales son fórmulas.
Si editás el LEDGER, todo recalcula solo.