## REASIGNAR
Fila master | WBS | Task title | Owner | MASTER Categoria (E) | MASTER Fase (F) | TD Categoria (B) | TD Fase (C) | TD Subfase (D) | Budget Revised | Spend | Diagnostico | → Categoria NUEVA | → Fase NUEVA
13 | 0.0001 | Due Diligence / Closing Costs | HOVDE | 0-Property Acquisition | Phase 1 | 0-Property Acquisition | P1 | Phase 1 | 803720.07 | 803720.07 | FASE DIFIERE
14 | 0.0002 | Property Acquisition | Partnership | 0-Property Acquisition | Phase 1 | 0-Property Acquisition | P1 | Phase 1 | 11250000 | 9382599.7 | FASE DIFIERE
18 | 0.1 | Property Interest | Partnership | Overhead | Phase 2 | Overhead | P2 | Overhead / Personnel | 787500 | 450000 | FASE DIFIERE
19 | 0.1.1 | Insurance | Partnership | Overhead | Phase 2 | Overhead | P2 | Overhead / Personnel | 20000 | 0 | FASE DIFIERE
20 | 0.1.2 | Titled Property Annual Taxes | Partnership | Overhead | Phase 2 | Overhead | P2 | Maintenance | 75000 | 0 | FASE DIFIERE
21 | 0.1.3 | Holding Corporation Taxes | Partnership | Overhead | Phase 2 | Overhead | P2 | Maintenance | 12600 | 6233.63 | FASE DIFIERE
22 | 0.2 | Concession/Land Use Leases | Partnership | Overhead | Phase 2 | Overhead | P2 | Maintenance | 87000 | 82507.5 | FASE DIFIERE
23 | 0.3 | Escrow and Legal Fees | Sergio Amador | Overhead | Phase 2 | Overhead | P2 | Maintenance | 50795.05 | 50795.05 | FASE DIFIERE
24 | 0.3.1 | Corporation Management | Sergio Amador | Overhead | Phase 2 | Overhead | P2 | Maintenance | 19686.1 | 19686.1 | FASE DIFIERE
25 | 0.4 | Admin Fee Budget + Financial Controller 25% Salary | Partnership | Overhead | Phase 2 | Overhead | P2 | Overhead / Personnel | 93750 | 71200 | FASE DIFIERE
26 | 0.5 | Travel Expenses / Ownership | Partnership | Overhead | Phase 2 | Overhead | P2 | Overhead / Personnel | 43641.38 | 43641.38 | FASE DIFIERE
27 | 0.6.1 | Farm Manager | Alexis | Overhead | Phase 2 | Overhead | P2 | Overhead / Personnel | 42334.4 | 20437.88 | FASE DIFIERE
28 | 0.6.2 | Farm Worker | TBD | Overhead | Phase 2 | Overhead | P2 | Overhead / Personnel | 16369.41 | 12068.23 | FASE DIFIERE
29 | 0.6.3 | CCSS Employee Benefits |  | Overhead | Phase 2 | Overhead | P2 | Overhead / Personnel | 18400 | 0 | FASE DIFIERE
30 | 0.6.4 | Main. Equip. / Expendables / Truck / Mula | Blake | Overhead | Phase 2 | Overhead | P2 | Overhead / Personnel | 62500 | 26043.39 | FASE DIFIERE
31 | 0.6.5 | Procore (If we want to implement is system) | Blake | Overhead | Phase 2 | Overhead | P2 | Overhead / Personnel | 21000 | 0 | FASE DIFIERE
32 | 0.7 | Development Director | Blake | Overhead | Phase 2 | Overhead | P2 | Overhead / Personnel | 393045 | 280045 | FASE DIFIERE
35 | 0.8 | Road Repairs | FyF | Overhead | Phase 2 | Overhead | P2 | Maintenance | 30000 | 0 | FASE DIFIERE
36 | 0.9 | Fallen Trees / Cutting Grass | Alexis/Gustavo | Overhead | Phase 2 | Overhead | P2 | Maintenance | 40000 | 2159.8 | FASE DIFIERE
37 | 0.911 | Property Gates | Blake | Overhead | Phase 2 | Overhead | P2 | Maintenance | 7400 | 8280.01 | FASE DIFIERE
40 | 1.1 | Gravel Existing Roads | FyF | Overhead | Phase 3 | Overhead | P3 | Maintenance | 80000 | 0 | FASE DIFIERE
41 | 1.2 | Opening Views | Tree Man Co. | Overhead | Phase 3 | Overhead | P2 | Maintenance | 52800 | 6820 | FASE DIFIERE
42 | 1.3 | Opening Paths to Important Areas | Alexis | Overhead | Phase 3 | Overhead | P2 | Maintenance | 6480 | 6480 | FASE DIFIERE
43 | 1.4 | Water System | Blake | Overhead | Phase 3 | Overhead | P3 | Maintenance | 205314.4 | 205447.3165 | FASE DIFIERE
47 | 2.1.1 | Pre Workshop | EDSA | CFIA Condo | DESIGN | CFIA Condo | DESIGN | DESIGN | 14500 | 0 | OK
48 | 2.1.2 | Workshop | EDSA | CFIA Condo | DESIGN | CFIA Condo | DESIGN | DESIGN | 54131.6 | 54131.6 | OK
49 | 2.1.3 | Post Workshop / Conceptual Enlargements | EDSA | CFIA Condo | DESIGN | CFIA Condo | DESIGN | DESIGN | 48500 | 7500 | OK
50 | 2.1.4 | Travel Expenses MP | EDSA | CFIA Condo | DESIGN | CFIA Condo | DESIGN | DESIGN | 5000 | 0 | OK
51 | 2.2 | Schematic Design | EDSA | CFIA Condo | DESIGN | CFIA Condo | DESIGN | DESIGN | 100000 | 0 | OK
54 | 3.1 | Preliminary environmental study, D1 form | DEHC | Setena D1 | STUDIES | Setena D1 | STUDIES | Phase 1 | 144577 | 141627.22 | OK
55 | 3.2 | Register Plans with Master Plan Roads | Surveyor | Setena D1 | ENGINEERING | Setena D1 | ENGINEERING | Phase 1 | 38702.5 | 38702.5 | OK
56 | 3.3 | Hydrological study / Discharge Permit | DEHC | Setena D1 | STUDIES | Setena D1 | STUDIES | Phase 1 | 8362 | 0 | OK
57 | 3.4 | Master plan analysis and condominium strategy | DEHC | Setena D1 | ENGINEERING | Setena D1 | ENGINEERING | Phase 2 | 12995 | 74 | OK
58 | 3.5 | Civil Engineering |  | Setena D1 | ENGINEERING | Setena D1 | ENGINEERING | Phase 2 | 0 | 0 | OK
59 | 3.5.1 | - Schematic design | DEHC | Setena D1 | ENGINEERING | Setena D1 | ENGINEERING | Phase 2 | 117068 | 35120.4 | OK
60 | 3.52 | - Construction drawings & quantities | DEHC | Setena D1 | ENGINEERING | Setena D1 | ENGINEERING | Phase 2 | 0 | 0 | OK
61 | 3.6 | SETENA review | Government | Setena D1 | ENGINEERING | Setena D1 | ENGINEERING | Phase 2 | 0 | 0 | OK
62 | 3.7 | Annexed information / Answer Questions | DEHC / Blake | Setena D1 | ENGINEERING | Setena D1 | ENGINEERING | Phase 2 | 0 | 0 | OK
63 | 3.8 | SETENA Final review | Blake | Setena D1 | GOV | Setena D1 | GOV | Phase 2 | 0 | 0 | OK
64 | 3.9 | SETENA (VA) Approval | DEHC / Blake | Setena D1 | ENGINEERING | Setena D1 | ENGINEERING | Phase 2 | 1457.7 | 0 | OK
65 | 3.101 | Treatment Plant | Treatment Plant Eng. | Setena D1 | GOV | Setena D1 | GOV | Phase 2 | 50000 | 0 | OK
66 | 3.11 | Superficial infiltration test | Complete | Setena D1 | GOV | Setena D1 | GOV | Phase 2 | 0 | 0 | OK
69 | 4.1 | Water Source Strategy | Blake | Setena D1 | WATER | Setena D1 | WATER | Phase 3 | 0 | 0 | OK
70 | 4.2.1 | Water Department Negotiations | Blake | Setena D1 | WATER | Setena D1 | WATER | Phase 3 | 0 | 0 | OK
71 | 4.2.2 | Water Department Installation (We pay and Donate) | Sierra | Setena D1 | WATER | Setena D1 | WATER | Phase 3 | 50000 | 0 | OK
72 | 4.2.3 | Water Department System Installation | Aguatech | Setena D1 | WATER | Setena D1 | WATER | Phase 3 | 150000 | 0 | OK
73 | 4.3 | Spring Concession (Based on Strategy) | Blake | Setena D1 | WATER | Setena D1 | WATER | Phase 3 | 0 | 0 | OK
74 | 4.4 | Deep Well Concession / Casing x 2 Wells | PV Drilling | Setena D1 | WATER | Setena D1 | WATER | Phase 3 | 126227 | 0 | OK
77 | 5.1 | Preliminar Study for PNE applications in ACOSA, SINAC, and Muni | Eduardo | Concessions | SETENA Regional Review | Concessions | SETENA Regional Review | SETENA Regional Review | 5000 | 0 | OK
78 | 5.2 | Engineering diagnosis to apply reversion of Patrimony areas to Muni ( to apply later for concessions ) | Eduardo consultant | Concessions | SETENA Regional Review | Concessions | SETENA Regional Review | SETENA Regional Review | 9944 | 0 | OK
79 | 5.3 | Application/ project description for PNE MINAET | Eduardo | Concessions | SETENA Regional Review | Concessions | SETENA Regional Review | SETENA Regional Review | 15876.5 | 0 | OK
80 | 5.4 | Survey new plans - Adjust to Government Regs | Surveyor | Concessions | SETENA Regional Review | Concessions | SETENA Regional Review | Survey | 72207 | 0 | OK
81 | 5.5 | Create Draft Plans for Development | Randall | Concessions | SETENA Regional Review | Concessions | SETENA Regional Review | SETENA Regional Review | 30000 | 0 | OK
82 | 5.6 | Legal Expenses - Concession MUNI | Herbet | Concessions | SETENA Regional Review | Concessions | SETENA Regional Review | MUNI Concession | 100000 | 0 | OK
83 | 5.7 | Legal Expenses - Land Use SINAC | Eduardo | Concessions | SETENA Regional Review | Concessions | SETENA Regional Review | MUNI Concession | 50000 | 0 | OK
84 | 5.8 | Legal Expenses - Land Use Concessions (ALTA BATALLA)} | Roberto | Concessions | SETENA Regional Review | Concessions | SETENA Regional Review | SINAC Land Use | 14500 | 0 | OK
87 | 6.1 | Trim Trees to See View | Tree Man Co. | Overhead | PROPERTY | Overhead | PROPERTY | Property | 7500 | 0 | OK
88 | 6.2 | Survey Water Easement and Register | Marvin | Overhead | PROPERTY | Overhead | PROPERTY | Property | 12950 | 10450 | OK
89 | 6.3 | Cut Driveway and Building Pad + Gravel + Culverts | Sibaja | Overhead | PROPERTY | Overhead | PROPERTY | Property | 40000 | 17583.15 | OK
90 | 6.4 | Closing Costs | Karol | Overhead | PROPERTY | Overhead | PROPERTY | Property | 48000 | 0 | OK
92 | 6 | Property Sale | Karol | Overhead | PROPERTY |  |  |  | -480000 |  | NO LLEGA AL TIMELINE
95 | 9.1.1 | Phase 1/2/3 Pre Consultations | DEHC | CFIA Infrastructure | Phase 1 | CFIA Infrastructure | P1 | Phase 1 | 5424 | 7345 | FASE DIFIERE
96 | 9.1.2 | Phase 1/2/3 Discharge permit MOPT and Municipality | DEHC | CFIA Infrastructure | Phase 2 | CFIA Infrastructure | P2 | Phase 2 | 1356 | 2034 | FASE DIFIERE
97 | 9.1.3 | Phase 1 Permit (Includes topo of the existing road) | DEHC | CFIA Infrastructure | Phase 1 | CFIA Infrastructure | P1 | Phase 1 | 16385 | 16385 | FASE DIFIERE
98 | 9.2.1 | Phase 2 Permit | DEHC | CFIA Infrastructure | Phase 2 | CFIA Infrastructure | P2 | Phase 2 | 8814 | 0 | FASE DIFIERE
99 | 9.3.1 | Phase 3 Permit | DEHC | CFIA Infrastructure | Phase 3 | CFIA Infrastructure | P3 | Phase 3 | 1356 | 0 | FASE DIFIERE
108 | 7.2 | Plan and approval of the two condominiums | Blake | CFIA Infrastructure | Phase 3 | CFIA Infrastructure | P3 | Phase 3 | 0 | 0 | FASE DIFIERE
109 | 7.3 | Cadastre Plan (only when we want to convey) | Surveyor | CFIA Infrastructure | Phase 3 | CFIA Infrastructure | P3 | Phase 3 | 102162.45 | 0 | FASE DIFIERE
110 | 7.4 | CFIA (1%) - Whole Project | Blake | CFIA Infrastructure | Phase 3 | CFIA Infrastructure | P3 | Phase 3 | 265000 | 0 | FASE DIFIERE
111 | 7.5 | INS (1.298%) - Phase Only | Blake | CFIA Infrastructure | Phase 3 | CFIA Infrastructure | P3 | Phase 3 | 129800 | 0 | FASE DIFIERE
112 | 7.6 | SETENA Bond (1.5% Value) - Phase Only | Partnership | CFIA Infrastructure | Phase 3 | CFIA Infrastructure | P3 | Phase 3 | 300000 | 0 | FASE DIFIERE
113 | 7.7 | Municipality (1%) - Phase Only | Permit Engineer | CFIA Infrastructure | Phase 3 | CFIA Infrastructure | P3 | Phase 3 | 100000 | 0 | FASE DIFIERE
117 | 8.1 | Water Department Negotiations | Blake | Setena D1 | Phase 1 | Setena D1 | Phase 1 | Phase 1 | 28250 | 0 | OK
118 | 8.2 | SETENA (VA) Approval | Blake | Setena D1 | Phase 1 | Setena D1 | Phase 1 | Phase 1 | 42375 | 0 | OK
119 | 8.3 | Finalize Creation of Concessions | Blake | Concessions |  | Concessions | SETENA Regional Review | MUNI Concession | 42375 | 0 | SIN FASE + FASE DIFIERE
120 | 8.4 | Obtain Beach Club Permits | Blake | Setena D1 | BEACH CLUB P1 | Setena D1 | BEACH CLUB P1 | Phase 1 | 14125 | 0 | OK

## CATALOGOS
Catalogo | Valor | Usos | Fuente
Categoria | Overhead | 22 | MASTER col E
Categoria | Setena D1 | 22 | MASTER col E
Categoria | CFIA Infrastructure | 11 | MASTER col E
Categoria | Concessions | 9 | MASTER col E
Categoria | CFIA Condo | 5 | MASTER col E
Categoria | Overhead | 5 | MASTER col E
Categoria | 0-Property Acquisition | 2 | MASTER col E
Fase | Phase 2 | 20 | MASTER col F
Fase | Phase 3 | 11 | MASTER col F
Fase | ENGINEERING | 8 | MASTER col F
Fase | SETENA Regional Review | 8 | MASTER col F
Fase | Phase 1 | 6 | MASTER col F
Fase | WATER | 6 | MASTER col F
Fase | DESIGN | 5 | MASTER col F
Fase | PROPERTY | 5 | MASTER col F
Fase | GOV | 3 | MASTER col F
Fase | STUDIES | 2 | MASTER col F
Fase | BEACH CLUB P1 | 1 | MASTER col F
Fase (Timeline) | P2 | 22 | TD col C
Fase (Timeline) | P3 | 9 | TD col C
Fase (Timeline) | SETENA Regional Review | 9 | TD col C
Fase (Timeline) | ENGINEERING | 8 | TD col C
Fase (Timeline) | WATER | 6 | TD col C
Fase (Timeline) | DESIGN | 5 | TD col C
Fase (Timeline) | P1 | 4 | TD col C
Fase (Timeline) | PROPERTY | 4 | TD col C
Fase (Timeline) | GOV | 3 | TD col C
Fase (Timeline) | STUDIES | 2 | TD col C
Fase (Timeline) | Phase 1 | 2 | TD col C
Fase (Timeline) | BEACH CLUB P1 | 1 | TD col C
Subfase (Timeline) | Phase 3 | 13 | TD col D
Subfase (Timeline) | Maintenance | 12 | TD col D
Subfase (Timeline) | Phase 2 | 12 | TD col D
Subfase (Timeline) | Phase 1 | 10 | TD col D
Subfase (Timeline) | Overhead / Personnel | 10 | TD col D
Subfase (Timeline) | DESIGN | 5 | TD col D
Subfase (Timeline) | SETENA Regional Review | 4 | TD col D
Subfase (Timeline) | Property | 4 | TD col D
Subfase (Timeline) | MUNI Concession | 3 | TD col D
Subfase (Timeline) | Survey | 1 | TD col D
Subfase (Timeline) | SINAC Land Use | 1 | TD col D